## Worksheet
Task | Start Date | End Date | Status | Responsible | Progress (%)
Destination Research & Selection | 2023-10-01 | 2023-10-05 | In Progress | Jane Smith | 75%
Flight Booking (Round Trip) | 2023-10-06 | 2023-10-10 | Completed | John Doe | 100%
Lodging Reservation (Hotel/Stay) | 2023-10-11 | 2023-10-15 | In Progress | Jane Smith | 60%
Travel Insurance Purchase | 2023-10-16 | 2023-10-18 | In Progress | Mike Johnson | 45%
Visa Application & Documentation | 2023-10-19 | 2023-10-25 | Delayed | Sarah Lee | 30%
Packing List & Preparation | 2023-10-26 | 2023-10-30 | In Progress | Jane Smith | 55%
Transportation Arrangements (Local) | 2023-10-31 | 2023-11-04 | In Progress | John Doe | 50%
Itinerary Finalization & Sharing | 2023-11-05 | 2023-11-07 | In Progress | Sarah Lee | 40%