## Worksheet
Travel Planning - Project Tracker (Detailed)
Task ID | Task Description | Assigned To | Status | Prioritization Level | Due Date | Budget (USD) | Milestones Reached | Notes / Remarks
T001 | Research destination options (3 countries) | Jane Doe | In Progress | High | 2025-04-15 | $1,200.00 | Country comparison matrix created. | Focused on cultural experiences and safety ratings.
T002 | Book flights (round-trip) | Mike Smith | Pending | High | 2025-04-30 | $1,850.00 | Flight search initiated. | Must consider layover times and baggage fees.
T003 | Reserve accommodation (7 nights) | Sarah Lee | In Progress | Medium | 2025-04-20 | $1,100.00 | 3 options shortlisted; reviews analyzed. | Prefers central location with free Wi-Fi.
T004 | Arrange travel insurance | David Kim | Pending | Medium | 2025-04-18 | $350.00 | Comparison of 3 providers in progress. | Must cover medical emergencies and trip cancellation.
T005 | Create daily itinerary (customized) | Jane Doe | Pending | High | 2025-05-10 | $0.00 (Time) | Itinerary template drafted. | Includes meals, sightseeing, and rest time.
T006 | Apply for necessary visas | Maria Gonzalez | Pending | High | 2025-04-25 | $380.00 (Application Fees) | Required documents list collected. | Processing time: 14 days after submission.
T007 | Purchase travel accessories (e.g., adapter, guidebooks) | Mike Smith | Pending | Low | 2025-04-28 | $120.00 | Purchase list compiled. | Include universal power adapter and pocket guide.
T008 | Finalize budget summary & approval | Jane Doe | Pending | High | 2025-04-14 | $6,000.00 Total (Est.) | Budget breakdown updated. | Requires sign-off from management.
Last Updated: April 5, 2025 ¦ Project Duration: April 1 – May 15, 2025