## Worksheet
Task | Start Date | End Date | Status | Assigned To | Budget (USD)(Estimated)(Actual) | Notes
Destination Research | 2023-10-01 | 2023-10-05 | In Progress | Jane Smith | $850 $795 | Compare top 3 destinations based on weather, cost, and attractions.
Flight Booking | 2023-10-06 | 2023-10-10 | Pending | Mark Johnson | $950 $- | Schedule flights with layovers under 3 hours.
Hotel Reservation | 2023-10-11 | 2023-10-15 | To Do | Sarah Lee | $750 $- | Book 5-star hotel within walking distance of main attractions.
Travel Insurance | 2023-10-16 | 2023-10-17 | To Do | Alex Brown | $180 $- | Compare policies for coverage and cost.
Itinerary Planning | 2023-10-18 | 2023-10-25 | To Do | Jane Smith, Mark Johnson | $50 $- | Create detailed daily plan including activities and meals.
Visa Application | 2023-10-26 | 2023-11-05 | To Do(Due: 7 days before departure) | Sarah Lee | $160 $- | Submit documents and pay fees online.
Packing List & Preparation | 2023-11-06 | 2023-11-15 | To Do | All Team Members | $75 $- | Compile checklist and confirm all items are packed.
Total | [5 empty] | $3,015 $795