## Worksheet
Travel Planning - Project Tracker
Task ID | Task Description | Assigned To | Status | Due Date | Priority
1. Planning Phase (Planning and Research)
TPL-001 | Define travel destination and purpose | Project Lead | Pending | 2023-11-15 | High
TPL-002 | Create initial travel budget estimate | Finance Coordinator | In Progress | 2023-11-18 | High
TPL-003 | Research visa requirements and travel restrictions | Travel Advisor | Pending | 2023-11-25 | Medium
TPL-004 | Identify potential accommodation options | Housing Team | Pending | 2023-11-28 | Medium
2. Logistics Phase (Booking and Coordination)
TPL-005 | Book flights and transportation | Logistics Coordinator | Pending | 2023-12-15 | High
TPL-006 | Reserve accommodation for full duration of trip | Housing Team | Pending | 2023-12-15 | High
TPL-007 | Arrange travel insurance and emergency contacts | Safety Officer | Pending | 2023-12-10 | Medium
3. Preparation Phase (Final Checks and Documentation)
TPL-008 | Confirm all reservations and itineraries | Project Lead | Pending | 2023-12-31 | High
TPL-009 | Prepare travel documents (passport, tickets, visas) | Documentation Team | Pending | 2024-01-05 | High
TPL-010 | Conduct final team briefing and safety orientation | Safety Officer | Pending | 2024-01-10 | High
Travel Planning - Project Tracker (Continued)
Task ID | Task Description | Assigned To | Status | Due Date | Priority
4. On-Travel Monitoring (During Trip Management)
TPL-011 | Track daily expenses and budget usage | Finance Coordinator | Pending | 2024-01-31 | Medium
TPL-012 | Monitor team safety and well-being daily | Safety Officer | Pending | 2024-01-31 | High
5. Post-Trip Phase (Reporting and Evaluation)
TPL-013 | Compile final trip report and feedback | Project Lead | Pending | 2024-02-15 | High
TPL-014 | Submit expense reconciliation and receipts | Finance Coordinator | Pending | 2024-02-20 | Medium
TPL-015 | Conduct post-trip debrief meeting and lessons learned session | Project Lead | Pending | 2024-02-25 | High
6. Additional Tracking Fields (Optional for Excel Integration)
TPL-016 | Update progress percentage | Project Lead | 0% | -- | --
Summary Metrics (Dashboard View)
Total Tasks | 22
Completed | 0 / 22 (0%)
In Progress | 1 / 22 (4.5%)
On Hold / Pending | 21 / 22 (95.5%)
Overall Progress |  |  |  | 0%
Legend
Pending | In Progress | Completed | Priority Labels: High (Red), Medium (Orange), Low (Yellow)