## Worksheet
Travel Planning Project Tracker - Report Version
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Budget (USD)
TASK-001 | Destination Selection & Research | Anna Johnson | 2024-04-15 | 2024-04-25 | In Progress | $850.00
TASK-002 | Flight Booking & Confirmation | Michael Chen | 2024-04-18 | 2024-05-15 | Pending | $1,350.00
TASK-003 | Hotel Reservations & Accommodation Confirmation | Sophia Williams | 2024-04-19 | 2024-05-18 | In Progress | $1,875.00
TASK-004 | Travel Insurance & Documentation Check | Liam Anderson | 2024-04-26 | 2024-05-13 | Pending | $385.00
TASK-005 | Local Transport Arrangements (Rental Cars, Trains) | Emma Brown | 2024-04-27 | 2024-05-16 | Pending | $695.00
TASK-006 | Itinerary Development & Sharing with Team | James Taylor | 2024-05-15 | 2024-05-31 | Pending | $175.00
TASK-007 | Emergency Plan & Contact List Finalization | Olivia Martinez | 2024-05-16 | 2024-05-31 | Pending | $75.00
TASK-008 | Final Review & Approval from Stakeholders | David Lee | 2024-05-31 | 2024-06-15 | Pending | $95.00
Total Project Budget: | [5 empty] | $5,600.00