## Travel Planning Project Tracker
Travel Planning Project Tracker
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Budget (USD)
T-001 | Finalize Travel Itinerary | Jane Doe | 2024-04-05 | 2024-04-15 | In Progress | $850.00
T-002 | Book Flights & Accommodation | Mark Lee | 2024-04-16 | 2024-05-10 | Pending | $1,350.00
T-003 | Arrange Local Transportation | Sarah Kim | 2024-05-11 | 2024-05-18 | To Do | $375.00
T-004 | Obtain Travel Insurance | Tom Wilson | 2024-05-19 | 2024-05-31 | To Do | $180.00
T-005 | Confirm Meeting Schedules with Clients | Lisa Chen | 2024-06-01 | 2024-06-15 | To Do | $50.00