## Worksheet
Travel Planning - Project Tracker (Tracking View)
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Budget Allocated ($)
T-001 | Research destination and visa requirements | Jane Doe | 2023-10-15 | 2023-10-25 | In Progress | 50
T-002 | Book flights and accommodations | John Smith | 2023-10-18 | 2023-11-15 | Pending | 1500
T-003 | Prepare travel insurance and medical documents | Jane Doe | 2023-11-16 | 2023-11-25 | Pending | 80
T-004 | Arrange local transportation and tours | Mike Brown | 2023-11-15 | 2023-11-30 | Pending | 400
T-005 | Finalize packing list and travel documents | Jane Doe | 2023-11-26 | 2023-12-05 | Pending | 20
T-006 | Travel to destination and begin trip | All Team Members | 2023-12-15 | 2023-12-31 | Pending | 0
Note:Status colors indicate progress:Pending— Not started,In Progress— Ongoing,Completed— Finished.