## Worksheet
Travel Planning Task Manager - Report Version
Project:International Adventure Trip 2024
Date Range:January 5, 2024 – March 31, 2024 ¦Generated on: April 5, 2024
Task ID | Task Description | Priority | Status | Due Date | Assigned To | Budget (USD)
TASK-001 | Finalize travel itinerary with destinations and flight times | High | Completed | 2024-01-15 | Emma Reynolds | 850
TASK-002 | Book international flights with layover options comparison | High | Pending | 2024-01-25 | Liam Carter | 1,980.00
TASK-003 | Research visa requirements for 6 destination countries | Medium | Pending | 2024-01-31 | Sophia Lee | 0
TASK-004 | Reserve 3-star accommodation in Paris, Rome & Tokyo for 7 nights each | High | Pending | 2024-02-15 | Noah Martin | 3,650.00
TASK-005 | Arrange travel insurance with medical and cancellation coverage | Medium | Pending | 2024-02-18 | Mia Thompson | 375
TASK-006 | Obtain passport renewal and update travel documents | High | Pending | 2024-01-28 | Oliver Bennett | 165
TASK-007 | Create packing list with climate-specific items and essentials | Low | Delayed (2 days) | 2024-01-30 | Isabella Rodriguez | 15
TASK-008 | Confirm transportation from airport to hotels in all cities | Medium | Pending | 2024-02-10 | Liam Carter & Sophia Lee | 575
TASK-009 | Collect traveler’s vaccinations and health documentation | High | Pending | 2024-02-14 | Emma Reynolds & Mia Thompson | 85
TASK-010 | Conduct final review meeting with travel team and update plan | High | Pending | 2024-03-15 | All Team Members | 0
© 2024 Travel Planning Task Manager ¦ Report Version ¦ Confidential – For Internal Use Only