## Worksheet
Travel Planning To-Do List - Financial View
Task | Category | Deadline | Status | Budget (USD) | Actual Cost (USD)
Research destination options | Planning | 2024-05-15 | Pending | $0.00 | $0.00
Book flights | Transportation | 2024-05-25 | Pending | $600.00 | $0.00
Reserve accommodations | Lodging | 2024-05-31 | Pending | $900.00 | $0.00
Buy travel insurance | Insurance | 2024-06-15 | Pending | $150.00 | $0.00
Arrange local transportation | Transportation | 2024-06-18 | Pending | $200.00 | $0.00
Purchase travel guidebooks & maps | Materials | 2024-06-18 | Pending | $50.00 | $0.00
Confirm all bookings and itineraries | Planning | 2024-06-25 | Pending | $0.00 | $0.00
Check passport & visa requirements | Documentation | 2024-06-15 | Pending | $0.00 | $0.00
Pack travel essentials and clothing | Preparation | 2024-06-30 | Pending | $100.00 | $75.50
Finalize daily itinerary and budget tracking sheet | Planning | 2024-07-01 | Pending | $50.00 | $35.75
Total Budgeted Amount: $2,150.00
Total Spent So Far: $111.25