## Worksheet
Workflow Stage | Responsible Team | Current Process Duration (Days) | Bottleneck Points | Efficiency Rate (%) | Proposed Optimization Action | Target Duration (Days) | Expected Efficiency Gain (%) | Resource Allocation | Risks & Mitigations
Requirement Gathering | Product & Stakeholder Management | 7 | Stakeholder misalignment, feedback delays | 65% | Introduce structured workshops and feedback templates | 4 | +18% | 2 FTEs (30 hrs/week) | Risk of stakeholder fatigue; mitigation via phased engagement
Design & Prototyping | UX & UI Design Team | 12 | Revisions due to stakeholder input | 58% | Implement agile sprints with clear design validation checkpoints | 8 | +24% | 3 FTEs (40 hrs/week) | Risk of scope creep; mitigation via design sign-off gates
Development & Coding | Engineering Team | 25 | Integration issues, dependency delays | 47% | Adopt CI/CD pipelines and modular architecture | 18 | +32% | 8 FTEs (50 hrs/week) | Risk of integration failures; mitigation via automated testing
Testing & QA | Quality Assurance Team | 14 | Bug density in early versions | 52% | Introduce automated test suites and parallel testing | 9 | +21% | 4 FTEs (40 hrs/week) | Risk of false positives; mitigation via test case refinement
Deployment & Launch | Operations & Release Team | 5 | Last-minute configuration issues | 78% | Implement pre-deployment checklists and rollbacks | 3 | +12% | 2 FTEs (30 hrs/week) | Risk of downtime; mitigation via failover plans
Post-Launch Monitoring | Support & Analytics Team | 10 | Incident response delays | 45% | Deploy real-time dashboards and incident escalation protocols | 6 | +28% | 3 FTEs (40 hrs/week) | Risk of user dissatisfaction; mitigation via proactive alerts