## Worksheet
Workflow Step | Responsible Party | Duration (Days) | Budget Allocation ($) | Key Metrics | Risk Assessment | Status
Requirement Gathering | Product & Stakeholder Team | 10 | $15,000 | Stakeholder alignment rate ≥85% | Low - Clear communication | On Track
Process Design & Flow Mapping | Process Optimization Team | 14 | $20,000 | Cycle time reduction by 15% | Medium - Dependency on IT | In Progress
Technology Integration | IT & Engineering Team | 18 | $45,000 | System uptime ≥99.5% | High - Data migration risk | Planned
Pilot Testing & Feedback Loop | Quality Assurance & Users | 12 | $18,000 | User satisfaction ≥4.5/5 | Low - Minor usability issues | Scheduled
Full-Scale Deployment | Operations & Leadership | 20 | $60,000 | Zero critical downtime | High - Change management complexity | Pending Approval
Post-Implementation Review & Optimization | Management & Analytics Team | 10 | $10,000 | Improvement rate ≥10% in KPIs | Low - Continuous monitoring | Not Started