## Worksheet
Activity | Responsible Party | Timeline | Resources Required | Budget Allocation ($) | KPIs / Metrics | Status
Workflow Assessment | Process Analyst Team | Week 1–2 | Surveys, Interviews, Data Collection Tools | 5,000 | Coverage Rate ≥90%, Accuracy ≥95% | On Track
Process Mapping | Operations Manager | Week 3–4 | Flowchart Software, Stakeholder Input | 8,000 | Process Clarity Score ≥8.5/10 | In Progress
Automation Identification | IT & Dev Team | Week 5–6 | RPA Tools, API Access, Scripting Resources | 12,000 | Automation Coverage ≥70% | Planned
Training & Change Management | HR & Change Lead | Week 7–8 | Training Materials, Workshops, Communication Plan | 6,000 | User Adoption Rate ≥85% | Pending Approval
Performance Review & Optimization | Executive Steering Committee | Week 9–10 | Analytics Dashboard, Feedback Loop Tools | 10,000 | Cycle Time Reduction ≥25% | Scheduled
Total Budget: |  |  | $41,000 |  | Approved for Analysis View