## Worksheet
Task | Responsible Party | Start Date | End Date | Estimated Duration (Days) | Budget Allocation ($) | Status
Requirement Gathering | Project Manager | 2024-03-01 | 2024-03-15 | 15 | 5,000 | In Progress
Process Mapping | Business Analyst | 2024-03-16 | 2024-03-31 | 15 | 4,500 | Planned
Workflow Design | Lead Designer | 2024-04-01 | 2024-04-15 | 15 | 6,000 | Pending Approval
Pilot Implementation | IT Team | 2024-04-16 | 2024-05-10 | 35 | 15,000 | Not Started
Performance Review & Optimization | Project Manager | 2024-05-11 | 2024-05-31 | 30 | 7,500 | Planned