## Worksheet
Activity | Responsible Party | Duration (Days) | Start Date | End Date | Budget Allocation ($) | Resource Requirements | Milestones | Risk Assessment | Approval Status
Workflow Audit & Analysis | Operations Manager | 15 | 2024-03-01 | 2024-03-15 | 5,000 | Team of 3 Analysts, Tools (Power BI, Visio) | Complete process mapping; Identify bottlenecks | Data access restrictions; Stakeholder resistance | Approved
Process Redesign & Workflow Mapping | Process Improvement Team | 25 | 2024-03-16 | 2024-04-10 | 12,500 | Workflow design software, Cross-functional workshops | Finalize redesigned workflows; Draft SOPs | Change in team structure; Tool compatibility issues | In Review
Technology Integration Planning | IT Department | 20 | 2024-04-11 | 2024-05-10 | 8,000 | System APIs, Integration testing environment | Define integration points; Validate data flow | System downtime risk; Legacy system dependencies | Pending
Pilot Implementation (Phase 1) | Operations & IT Joint Team | 30 | 2024-05-11 | 2024-06-10 | 15,000 | Pilot team, monitoring dashboard, training modules | Successful execution; User adoption > 85% | User error during transition; Incomplete training | Approved
Full-Scale Rollout & Training | HR & Department Heads | 45 | 2024-06-11 | 2024-08-15 | 30,000 | Training sessions, Helpdesk support, Onboarding kits | All departments adopt new workflow; KPIs meet targets | Unexpected workload spikes; Training fatigue | In Progress
Post-Implementation Review & Optimization | Executive Steering Committee | 10 | 2024-08-16 | 2024-08-25 | 3,500 | Performance data analysis, feedback survey | Identify 2 areas for further optimization | Data inconsistencies; Survey response bias | Scheduled