## Worksheet
Workflow Step | Responsible Team | Timeline (Months) | Budget Allocation ($) | Key Deliverables | KPIs & Metrics | Risks & Mitigations | Review Frequency
Requirement Gathering | Product & Stakeholder Teams | 1-2 | $15,000 | Stakeholder needs documented, user stories finalized | 90% stakeholder alignment rate | Unclear priorities → Conduct prioritization workshop | Bi-monthly
Process Mapping & Analysis | Operations & Process Team | 2-3 | $20,000 | Current workflows documented, bottlenecks identified | 30% reduction in cycle time target | Data access issues → Secure cross-departmental access | Monthly
Automation & Tool Selection | IT & DevOps Team | 3-4 | $45,000 | Automated workflows deployed, tools validated | 95% process accuracy post-automation | Tool integration delays → Use phased rollout | Quarterly
Pilot Implementation | Product & Operations Teams | 4-5 | $30,000 | Pilot process tested in one department | 10% improvement in efficiency measured | User resistance → Provide training and support | Bi-weekly
Full-Scale Deployment | All Departments | 5-6 | $60,000 | Workflow optimized across all units | Overall cycle time reduced by 25% | System downtime → Implement backup protocols | Monthly
Performance Review & Optimization | Management & Analytics Team | 6-7+ | $10,000 (Ongoing) | Continuous improvement plan updated | Monthly KPI reporting & trend analysis | Changing priorities → Reassess quarterly | Monthly
Total Budget Allocation: |  |  |  | $180,000