## Worksheet
Activity | Responsible Party | Estimated Duration (Days) | Budget Allocation ($) | Status | Progress (%)
Requirements Gathering | Project Manager & Stakeholders | 10 | 5,000 | On Track | 85%
Process Mapping | Process Analysts | 14 | 6,500 | In Progress | 45%
Workflow Design & Prototyping | Design Team | 20 | 10,000 | Not Started | 0%
Technology Integration Planning | IT Department | 12 | 8,000 | Pending Approval | -
Training & Change Management | HR & Training Unit | 8 | 3,000 | Planned | 0%
Total Budget |  |  | 32,500 | Overall Progress: 55%