## Worksheet
Task | Responsible Party | Estimated Time (hrs) | Budget Allocation ($) | Status | Deadline
Project Scope Definition | Freelancer A | 5 | 200 | In Progress | 2024-04-15
Workflow Process Mapping | Freelancer B | 8 | <350 | Planned | 2024-04-25
Stakeholder Alignment Meeting | Freelancer C | 3 | 150 | Scheduled | 2024-04-18
Optimization Strategy Design | Freelancer A & B | 10 | 500 | Not Started | 2024-05-10
Performance Metrics Setup | Freelancer D | 6 | 250 | Planned | 2024-05-05