## Worksheet
Task | Responsible Party | Deadline | Budget Allocation ($) | Status | Comments
Workflow Assessment & Analysis | Project Manager | 2024-03-31 | 5,000 | On Track | Initial process mapping completed.
Process Redesign Proposal | Design Team | 2024-04-15 | 8,000 | In Progress | Finalizing workflow diagrams.
Stakeholder Review & Feedback | Operations Lead | 2024-04-30 | 6,500 | Pending | Awaiting feedback from department heads.
Implementation Planning | IT Department | 2024-05-15 | 9,000 | Not Started | Needs technical feasibility review.
Pilot Run & Performance Evaluation | Quality Assurance Team | 2024-06-30 | 7,500 | Not Started | To be scheduled after approval.