## Worksheet
Activity | Responsible Party | Timeline | Resources Required | Budget Allocation (USD) | Status
Workflow Audit & Gap Analysis | Operations Manager | Week 1-2 | Internal Review Team, Data Collection Tools | 5,000 | In Progress
Process Mapping & Standardization | Process Engineers | Week 3-4 | Flowchart Software, Staff Time | 8,000 | Not Started
Automation Implementation | IT Department | Week 5-8 | RPA Tools, Cloud Infrastructure | 20,000 | Planned
Training & Change Management | HR & Department Heads | Week 9-10 | Workshops, Training Materials | 6,500 | Not Started
Performance Review & KPIs Setup | Analytics Team | Week 11-12 | Dashboard Tools, Data Access | 4,000 | Planned
Review & Final Optimization | Executive Committee | Week 13 | Stakeholder Meetings, Reports | 2,500 | Not Started
Total Budget: |  |  |  | 46,000