## Worksheet
Activity | Responsible Party | Start Date | End Date | Resources Required | Budget Allocation ($) | Status | Key Deliverables
Requirement Gathering | Product Manager | 2024-03-01 | 2024-03-15 | Stakeholders, Interviews | 5,000 | On Track | Identified core user needs
Process Mapping | Operations Lead | <+103>2024-03-162024-04-05 | Process documentation tools | 8,500 | In Progress | Visual workflow diagrams completed
Solution Design | Design Team | 2024-04-06 | 2024-05-10 | UI/UX Designers, Prototypes | 15,000 | Planned | Wireframes and mockups ready
Development & Integration | Engineering Team | 2024-05-11 | 2024-07-30 | Backend, Frontend developers, DevOps | 75,000 | On Track | System fully integrated and tested
Testing & Quality Assurance | QA Manager | 2024-08-01 | 2024-08-25 | Testers, Automation Tools | 12,000 | Scheduled | Bug fixes and regression tests completed
Deployment & Go-Live | IT Operations | 2024-08-26 | 2024-08-31 | Cloud infrastructure, Support team | 10,000 | Pending | System live and monitoring active
Total Budget Allocation: $125,500