## Worksheet
Quarter | Activity | Responsible Team | Timeline (MM/YY) | Budget Allocation ($) | Status | Notes
Q1 2024 | Process Audit & Gap Analysis | Operations & Compliance | 01/2024 – 03/2024 | $15,000 | Pending Approval | Initial workflow mapping completed.
Q1 2024 | Tool Integration Planning | IT & Digital Transformation | 02/2024 – 03/2024 | $8,500 | In Progress | Vendor shortlist finalized.
Q2 2024 | Workflow Automation Pilot | Engineering & Operations | 04/2024 – 06/2024 | $35,000 | Planned | Focused on approval workflows.
Q2 2024 | Training & Change Management | HR & Change Office | 05/2024 – 07/2024 | $18,000 | Pending Approval | Need to align with employee feedback.
Q3 2024 | Performance Metrics Implementation | Analytics & Finance | 08/2024 – 10/2024 | <$12,500 | Not Started | KPIs to be defined by Q3.
Q4 2024 | Full Workflow Optimization Review | Executive Leadership & Ops | 11/2024 – 01/2025 | $30,000 | Planned | Final reporting and cost-benefit analysis.