## Worksheet
Activity | Responsible Party | Timeline | Resources Required | Estimated Cost ($) | Status
Needs Assessment | Operations Manager | Week 1-2 | Surveys, Interviews | 500 | In Progress
Process Mapping | Process Analyst | Week 3-4 | Flowcharts, Tools | 800 | Planned
Identify Bottlenecks | Operations Manager | Week 5-6 | Data Analysis | 600 | Not Started
Propose Process Improvements | Project Team | Week 7-8 | Templates, Tools | 1,200 | Planned
Pilot Implementation | Operations Team | Week 9-10 | Training, Tools | 1,500 | Not Started
Review & Scale | Executive Sponsor | Week 11-12 | Performance Metrics | 700 | Pending Review