## Worksheet
Activity | Responsible Party | Timeline | Budget (USD) | Status | Notes
Market Research & Analysis | Product Team | Week 1–3 | $5,000 | On Track | Includes competitor benchmarking and customer surveys.
Product Roadmap Planning | CEO & CPO | Week 4–5 | <$3,000 | In Progress | Finalizing MVP features based on research.
UI/UX Design Phase | Design Team | Week 6–8 | $8,000 | Planned | Focus on user journey mapping and prototyping.
Development Sprint (MVP) | Engineering Team | Week 9–16 | $25,000 | Not Started | Agile sprints with bi-weekly reviews.
Beta Testing & Feedback Loop | Product & QA Teams | Week 17–20 | $6,500 | Pending Approval | Target 500 early adopters for feedback.
Go-to-Market Launch | Marketing & Sales | Week 21–24 | $15,000 | Not Started | Include PR, ads, and sales enablement kits.