## Worksheet
Week | Activity | Responsible Person | Estimated Time (hrs) | Budget Allocation ($) | Status | Notes
Week 1 | Workflow Audit & Gap Analysis | Jane Smith | 8 | 1,200 | Planned
Week 2 | Process Mapping & Documentation | Mark Johnson | 10 | 1,500 | In Progress | Initial drafts completed.
Week 3 | Stakeholder Review & Feedback | Lisa Brown | 6 | 900 | Pending | Waiting for approval from senior team.
Week 4 | Optimization Implementation Plan | David Lee | 12 | 2,000 | Not Started | To be finalized based on feedback.
Week 5 | Training & Change Management | Team Lead | 14 | 2,500 | Planned | All departments to participate.
Weekly Budget Summary – Workflow Optimization
Total Hours | 50 |  |  | $7,100