## Worksheet
Workflow Phase | Objective | Key Activities | Responsible Party | Timeline (MM/YY) | KPIs & Metrics | Risks & Mitigations
Initiation | Define workflow scope, stakeholders, and goals | Stakeholder workshops, requirement gathering, scope validation | Project Sponsor & Process Owner | 03/2024 | Stakeholder alignment rate ≥90% | Scope creep – mitigation via change control board
Design & Modeling | Map current and proposed workflows using process models | Process mapping, flowchart development, gap analysis | Process Analyst & IT Team | 04/2024 – 05/2024 | Process efficiency improvement target of 15% | Inaccurate modeling – mitigation via peer review and validation sessions
Implementation | Deploy new workflow in pilot department | System configuration, user training, data migration | IT Operations & Training Manager | 06/2024 – 07/2024 | Pilot completion rate ≥95% | User resistance – mitigation via change management program
Evaluation & Optimization | Measure performance, identify bottlenecks, and refine | Performance audits, feedback collection, continuous improvement cycles | Process Owner & Performance Team | 08/2024 – 12/2024 | Cycle time reduction ≥20%, error rate ≤3% | System downtime – mitigation via redundant processes