## Worksheet
Section | Objective | Key Activities | Responsible Party | Timeline | Success Metrics
1. Current Workflow Assessment | Identify inefficiencies and bottlenecks in existing processes. | Process mapping, stakeholder interviews, data collection. | Operations Manager | Weeks 1–2 | % of time spent on non-value-added tasks reduced by 20%
2. Process Redesign & Standardization | Develop optimized workflows based on assessment findings. | Design new workflows, draft SOPs, conduct pilot testing. | Process Improvement Team | Weeks 3–6 | 90% of team members agree on clarity and ease of use (survey)
3. Training & Change Communication | Ensure all staff understand and adopt new workflows. | Develop training materials, conduct workshops, provide support. | HR & Department Heads | Weeks 7–8 | 100% of staff complete training; 95% report confidence in new process
4. Implementation & Monitoring | Roll out the new workflow and monitor performance. | Deploy changes, track KPIs, collect feedback. | Operations Manager & IT | Weeks 9–12 | Reduction in cycle time by 15%; error rate down by 10%
5. Review & Continuous Improvement | Evaluate outcomes and refine workflows over time. | Performance reviews, feedback analysis, process updates. | Executive Committee | Ongoing | Quarterly review of efficiency gains and employee satisfaction