## Worksheet
Workflow Step | Responsible Employee | Deadline | Status | Notes/Remarks
Initiate Project Proposal | Project Manager | 2024-03-15 | Completed | Proposal submitted and approved by department head.
Define Workflow Process Map | Process Analyst | 2024-03-20 | In Progress | Finalizing process steps with cross-functional teams.
Assign Tasks to Team Members | Team Lead | 2024-03-25 | Pending | Waiting for team availability confirmation.
Conduct Workflow Review Meeting | All Team Members | 2024-03-30 | Not Started | Meeting agenda to be distributed by 3/25.
Document Updated Process Guidelines | Operations Specialist | 2024-04-05 | Not Started | Final draft to be reviewed by compliance team.
Train Employees on New Workflow | HR Coordinator | 2024-04-10 | Scheduled | Training session scheduled for 9:00 AM, 4/10.