## Worksheet
Workflow Step | Responsible Party | Timeline (Days) | Input Requirements | Output Deliverables | Success Metrics | Risks & Mitigation | Dependencies
Requirement Gathering | Business Analysts | 7 | Stakeholder interviews, process maps | Detailed requirements document | 90% stakeholder agreement on requirements | Incomplete input → Schedule follow-up meeting | Final approval from Product Manager
Process Design & Mapping | Process Engineers | 10 | Requirements document, business rules | Visual workflow diagrams (BPMN) | Clear identification of bottlenecks | Design conflicts → Cross-functional review | Requirement validation from Operations Team
Tool Selection & Integration | IT Department | 14 | Workflow specifications, security policies | Integrated automation platform with access logs | System uptime ≥ 99.5% | Vendor delays → Contingency plan activated | Approval from CTO and Compliance Officer
Pilot Implementation | Project Team | 18 | Final design, test data set | Pilot report with performance metrics | 20% improvement in cycle time | User resistance → Training session scheduled | Stable test environment from DevOps team
Full-Scale Rollout | Operations & Leadership | 21 | Pilot results, training materials | Go-live announcement, full workflow operationalization | Zero critical defects in first 30 days | System failures → On-call support team activated | Approval from Executive Leadership
Post-Implementation Review | Business Analysts & Managers | 7 | Performance data, user feedback | Review report with optimization recommendations | 15% efficiency gain over baseline | Data gaps → Additional data collection plan | Monthly performance tracking from Finance Team