## Worksheet
Activity | Responsible Party | Timeline (Months) | Resource Allocation | Budget (USD) | KPIs | Risk & Mitigation
Workflow Assessment | Operations Lead | 1 | Internal Audit Team | 25,000 | 90% process clarity, 85% efficiency gain | Stakeholder resistance - Engagement plan implemented
Process Mapping | Process Analysts | 2 | Business Process Tools, Staff Time | 40,000 | Complete flow diagrams for all key workflows | Data availability delay - Backup data sources identified
Automation Implementation | IT & Engineering Team | 4 | Automation Software, Dev Resources | 120,000 | 85% reduction in manual steps, 40% time saving | System integration failure - Phased rollout with testing
Training & Change Management | HR & Change Manager | 3 | Training Budget, Internal Facilitators | 35,000 | 95% staff trained, 90% adoption rate | Low engagement - Gamification and feedback loops introduced
Performance Review & Optimization | Operations & Finance Teams | 6 | Analytics Tools, Cross-functional Team | 50,000 | +25% efficiency, -15% operational cost | External dependency - Contingency plan with alternate vendors