## Worksheet
Activity | Responsible Party | Timeline | Deliverables | Success Metrics
Define Workflow Goals | Project Manager & Stakeholders | Week 1 - Week 2 | Workflow objectives document | % alignment with business goals (≥90%)
Map Current Processes | Process Analyst & Team Leads | Week 3 | Process flow diagrams (PDF & Visio) | 100% of key steps documented
Identify Bottlenecks | Operations Team & Data Analysts | Week 4 | Bottleneck analysis report | >85% of delays attributed to identifiable issues
Design Optimized Workflow | Product & Engineering Team | Week 5 - Week 6 | Digital workflow prototype (Figma) | End-to-end process reduces time by ≥20%
Implement Workflow | Operations & IT Support | Week 7 - Week 8 | Live workflow deployment with training materials | All teams trained and operational within 3 days
Monitor & Review Performance | Project Manager & Metrics Team | Ongoing (Monthly) | Performance dashboards, monthly reports | Process cycle time reduced by ≥15% month-over-month