## Worksheet
Workflow Step | Responsible Party | Timeline (Days) | Key Deliverables | Success Metrics | Risks & Mitigations
Requirement Gathering | Product Owner, Stakeholders | 5 | Comprehensive workflow documentation, stakeholder input summary | % of stakeholders who provide timely feedback ≥ 90% | Risk: Stakeholder unavailability – Mitigation: Schedule virtual syncs and assign alternates
Process Mapping | Business Analyst, Operations Lead | 3 | Visual workflow diagram (flowchart), process breakdown by stage | 95% accuracy in identifying current process bottlenecks | Risk: Incomplete data – Mitigation: Cross-validate with operational logs and interviews
Optimization Design | Design Team, Project Manager | 7 | Draft optimized workflow, proposed automation rules | Reduction of manual steps by ≥ 30% | Risk: Poor user adoption – Mitigation: Conduct usability testing with early users
Pilot Implementation | IT Team, Process Owner | 10 | Pilot workflow run, performance logs, user feedback report | Zero critical errors during pilot; 90% process completion rate | Risk: Integration failure – Mitigation: Conduct pre-deployment integration tests
Full-Scale Rollout | Operations, All Departments | 15 | Official go-live, training materials, post-implementation review | 20% reduction in cycle time; 95% user satisfaction (post-rollout survey) | Risk: Resistance to change – Mitigation: Launch change management program with communication plan