## Worksheet
Section | Key Objective | Process Steps | Responsible Party | Timeline (Weeks) | KPIs & Metrics
1. Needs Assessment | Identify current workflow inefficiencies and pain points. | - Conduct stakeholder interviews - Analyze existing process maps - Gather performance data | Operations Team & Process Analyst | Weeks 1–2 | % of bottlenecks identified, employee feedback score (1–5)
2. Process Mapping | Document and visualize current end-to-end workflows. | - Create workflow diagrams - Identify handoffs, delays, and redundancies - Classify key decision points | Process Designer & IT Support | Weeks 3–4 | Number of identified process loops, clarity score (1–10)
3. Optimization Design | Develop streamlined, efficient workflows based on analysis. | - Redesign process flow - Introduce automation where applicable - Propose standardization rules | Business Unit Leaders & Tech Team | Weeks 5–6 | Reduction in processing time, % of manual steps eliminated
4. Pilot Implementation | Test the optimized workflow in a controlled environment. | - Run pilot for 2 weeks - Monitor performance and user feedback - Adjust based on results | Project Manager & Operations Team | Weeks 7–8 | Pilot success rate, error reduction, user satisfaction (NPS)
5. Full-Scale Rollout | Deploy optimized workflow across all departments. | - Training sessions for staff - System integration and support - Monitoring system in real-time | Leadership & HR Team | Weeks 9–12 | Time-to-completion reduction, user adoption rate, system uptime
Workflow Optimization – Business Plan (Office Use)