## Worksheet
Quarter | Objective | Key Activities | Resources Required | Milestones | Success Metrics | Risks & Mitigation
Q1 | Establish baseline workflow performance | Conduct process mapping, employee interviews, system audits | Process analysis tools, HR support, data access permissions | Complete workflow inventory; identify bottlenecks | 60% reduction in manual documentation; 90% process clarity | Resistance to change – mitigation via training workshops
Q2 | Optimize high-impact workflows | Redesign key processes, implement automation tools | Automation software (e.g., RPA), IT support, project manager | Automated process live in 3 core areas; performance improvement report | 15% faster turnaround time; 20% cost reduction | System integration failures – mitigation via phased testing
Q3 | Scale optimized workflows across departments | Training rollout, process standardization, cross-departmental reviews | Training materials, department heads, change management team | All departments adopt updated workflows; feedback survey completed | 85% staff adoption rate; consistent KPI improvements | Staff workload imbalance – mitigation via role realignment
Q4 | Evaluate performance and plan next phase | Performance review, ROI analysis, future roadmap development | Finance team, analytics software, executive leadership | Final performance report; approved Q1 roadmap for next year | Overall efficiency gain of at least 25%; ROI > 1.5x | Unexpected market changes – mitigation via agile adjustment plans