## Worksheet
Section | Objective | Key Activities | Responsible Party | Timeline | KPIs & Metrics
1. Workflow Audit | Identify current processes and inefficiencies. | Conduct process mapping, gather stakeholder input, analyze bottlenecks. | Operations Manager & Process Analyst | Week 1–2 | Number of identified bottlenecks, process cycle time before/after
2. Process Redesign | Redesign workflows to eliminate redundancies and improve flow. | Develop new process diagrams, conduct pilot testing, document standard operating procedures. | Process Improvement Team | Week 3–6 | Reduction in task completion time by at least 20%, error rate reduction
3. Technology Integration | Implement tools to automate repetitive tasks. | Select and deploy automation software, train staff, integrate with existing systems. | IT Department & Change Management Lead | Week 4–8 | % of automated tasks, system uptime, user adoption rate
4. Staff Training & Change Management | Ensure all employees understand and adopt new workflows. | Develop training materials, conduct workshops, provide ongoing support. | HR Department & Department Heads | Week 5–10 | Training completion rate, employee satisfaction survey scores
5. Performance Review & Optimization | Evaluate outcomes and refine processes continuously. | Collect feedback, review KPIs, conduct quarterly reviews. | Executive Steering Committee | Ongoing (Quarterly) | Process efficiency improvement rate, cost savings achieved