## Worksheet
Section | Objective | Key Activities | Responsible Party | Timeline
1. Workflow Assessment | Identify current processes and bottlenecks. | Process mapping, stakeholder interviews, data collection. | Operations Manager | Week 1–2
2. Process Redesign | Optimize workflows for efficiency and scalability. | Develop flowcharts, eliminate redundancies, standardize tasks. | Process Improvement Team | Week 3–4
3. Technology Integration | Implement tools to support automation and tracking. | Select software, configure systems, train staff. | IT Department | Week 5–6
4. Pilot Implementation | Test redesigned workflow in a controlled environment. | Run pilot phase, collect feedback, monitor KPIs. | Operations & IT | Week 7–8
5. Full Rollout | Deploy optimized workflow across all departments. | Communication plan, training sessions, support system. | Executive Leadership | Week 9–10
6. Performance Review | Evaluate outcomes and identify areas for further improvement. | Analyze KPIs, conduct reviews, document lessons learned. | Management Team | Week 11–12