## Worksheet
Workflow Step | Responsible Team | Timeline (Days) | Key Deliverables | Success Metrics | Risks & Mitigations
Requirement Gathering | Product & UX Team | 7 | User personas, workflow maps, feature list | 90% stakeholder alignment on requirements | Scope creep – enforce change control process
Process Design & Flow Mapping | Operations & Process Team | 10 | Visual workflow diagrams, touchpoint analysis | Reduction of bottlenecks by 20% | Inadequate stakeholder input – conduct workshops
Pilot Implementation | Dev & QA Team | 14 | Prototype version, user testing report | 85% usability score in testing phase | Technical debt – plan iterative fixes
Full-Scale Rollout | All Teams (with Ops Lead) | 21 | Go-live plan, training materials, monitoring dashboard | 95% system uptime & 30% faster processing time | Change resistance – deploy change management program
Performance Review & Feedback Loop | Management & Analytics Team | 5 | Post-implementation review, KPI dashboard update | Identify at least 2 improvement opportunities | Data availability delays – schedule weekly syncs