## Worksheet
Workflow Stage | Responsible Team | Key Activities | Timeline (Days) | KPIs & Metrics | Risks & Mitigation | Status
Initiation | Strategy & Planning | Define objectives, scope, and stakeholders. | 5 | Stakeholder alignment rate ≥90% | Low engagement – Schedule kick-off meeting | On Track
Requirement Gathering | Operations & Product Teams | Collect process inputs, outputs, and constraints. | 7 | Completion rate of 100% for all key processes | Data gaps – Conduct validation sessions | On Schedule
Process Mapping | Process Design Team | Visualize current workflows using flowcharts. | 6 | Accuracy of mapping ≥95% | Inconsistencies – Cross-check with frontline staff | On Track
Optimization Design | Analytics & Engineering | Identify bottlenecks and propose improvements. | 10 | Reduction in cycle time by ≥20% | Resource constraints – Prioritize high-impact changes | In Progress
Pilot Implementation | Operations & IT Support | Deploy changes in a controlled environment. | 14 | Error rate ≤3% during pilot | Change resistance – Conduct training sessions | Planned
Full-Scale Rollout | All Departments | Roll out optimized workflows across departments. | 21 | Overall process efficiency increase by ≥30% | Integration delays – Use phased rollout | Not Started