## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Completion Time (hrs) | Key Metrics | Notes & Actions
Initiate Request | Customer Service Manager | 01/15/2024 | Completed | 0.5 | Request received & validated | No pending actions
Validate Workflow Requirements | Operations Lead | 01/18/2024 | In Progress | 1 | Review process alignment with KPIs | Update workflow documentation by end of week
Assign Tasks & Resources | Project Coordinator | 01/20/2024 | Pending | 1.5 | Resource availability confirmed | Notify team members via email
Execute Workflow Process | Process Team | 01/25/2024 | Not Started | - | Target throughput of 90% | Set up tracking dashboards
Review & Optimize | Strategy Director | 01/30/2024 | Planned | 2 | Cycle time reduction target | Propose revised workflow in Q1 report