## Worksheet
Workflow Step | Responsibility | Duration (Days) | Key Metrics | Dependencies | Risk Level | Optimization Action
Initiation & Assessment | Project Manager | 3 | Stakeholder alignment, feasibility score ≥80% | None | Low | Define clear KPIs early
Requirement Gathering | Business Analysts | 5 | Completion rate ≥95%, 3+ stakeholder reviews | Initiation & Assessment | Medium | Use standardized templates and surveys
Design & Planning | UX & Engineering Teams | 7 | Design approval rate, timeline adherence | Requirement Gathering | Medium-High | Implement agile sprints and design reviews
Development & Execution | Development Team | 20 | Code quality, defect rate & sprint velocity | Design & Planning | High | Automate testing and CI/CD pipelines
Testing & Validation | QA Team | 6 | Defect closure rate, user acceptance rate | Development & Execution | Medium | Introduce parallel testing environments
Deployment & Rollout | Operations & PM | 2 | Uptime ≥99.5%, user feedback within 48h | Testing & Validation | Low-Medium | Roll out in phased segments with monitoring
Monitoring & Review | All Teams | Ongoing | Performance trends, user satisfaction (CSAT) | Deployment & Rollout | Low | Monthly retrospective and continuous improvement