## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Remarks
Requirement Gathering | Product Owner, Stakeholders | 2024-03-15 | Completed | Finalized user needs and business goals.
Process Mapping | Business Analyst | 2024-03-20 | In Progress | Current workflow diagrams under review.
Process Automation Proposal | IT Team, Operations Manager | 2024-04-05 | Pending Review | Suggested tools and integration points.
Stakeholder Approval | Executive Sponsor | 2024-04-10 | Not Started | All documents ready for sign-off.
Implementation Phase | Development & Operations Teams | 2024-05-01 | Planned | Pilot run scheduled for Q2.