## Worksheet
Workflow Step | Responsible Party | Deadline | Input Requirements | Output Deliverables | KPIs & Metrics | Risks & Mitigations | Approval Required?
Workflow Initiation | Project Manager | Day 1 | Project scope, stakeholder list, budget outline | Workflow charter document | Scope clarity score ≥ 90% | Stakeholder misalignment – weekly alignment meeting | Yes
Requirement Gathering | Business Analysts | Day 5 | Stakeholder interviews, process mapping templates | Detailed requirement document (v1.0) | Requirement completeness = 95% | Incomplete inputs – follow-up with stakeholders | Yes
Process Design & Mockup | Design Team | Day 10 | Requirement document, user personas | Process flow diagrams, user journey map | Design usability score ≥ 85% | Design inconsistency – peer review process | Yes
Development & Implementation | Engineering Team | Day 20 | Approved process designs, API specs | Functional software module(s) | Bug rate ≤ 3% per sprint | Scope creep – change control board review | Yes
Testing & Validation | QA Team | Day 25 | Development build, test cases | Test report with pass/fail status, defect log | Defect resolution rate ≥ 98% | Critical bugs – immediate fix and retest | Yes
Deployment Planning | Operations Lead | Day 28 | Final test report, rollback plan | Deployment schedule & rollout plan | Uptime ≥ 99.5% post-deployment | Infrastructure failure – backup server ready | Yes
Go-Live & Monitoring | Operations & Support Team | Day 30 | Deployment plan, monitoring tools | Live system status report, incident log | Average response time ≤ 2 seconds | User feedback issues – real-time support escalation | Yes
Post-Implementation Review | Project Manager & Steering Committee | Day 35 | Live system data, user feedback forms | Post-implementation review report (PIR) | User satisfaction ≥ 80% | Unexpected performance gaps – root cause analysis | Yes