## Worksheet
Workflow Step | Responsible Party | Deadline | Inputs Required | Outputs Delivered | KPIs & Metrics | Risk Assessment | Approval Required?
Initiation & Stakeholder Alignment | Project Manager | Day 1 | Business objectives, stakeholder list | Stakeholder engagement plan, workflow scope document | 90% stakeholder agreement within first week | Low – misalignment with expectations | Yes
Process Mapping & Analysis | Business Analyst | Day 5 | Current workflow documentation, process logs | Process flow diagram, pain point report | 30% reduction in cycle time identified | Medium – data gaps in legacy system | Yes
Solution Design & Prototyping | Product Team & UX Designer | Day 10 | Process analysis report, stakeholder feedback | Wireframes, prototype model, user flow map | User satisfaction score ≥ 4.0/5.0 | High – change resistance from legacy teams | Yes
Pilot Testing & Feedback Loop | Operations Team & QA Lead | Day 15 | Prototype, user guide, test environment access | Test results summary, usability score report | Error rate ≤ 5%, task completion time reduced by ≥15% | Medium – intermittent system downtime | Yes
Full-Scale Implementation | IT Department & Project Manager | Day 25 | Pilot results, training materials, deployment plan | Go-live announcement, system access logs | 99.5% uptime post-launch | High – integration with external systems | Yes
Post-Implementation Review & Optimization | Project Manager & Operations Lead | Day 30 | Performance data, user feedback forms | Optimization report, continuous improvement plan | Cycle time reduced by ≥20% from baseline | Low – minor usability improvements needed | Yes