## Worksheet
Step | Activity | Responsible Party | Deadline | Status | Notes
1 | Project Scope Finalization | Project Manager | May 3, 2024 | Completed | Approved by stakeholders.
2 | Workflow Design & Mapping | Process Analyst | May 10, 2024 | In Progress | Reviewing user feedback.
3 | Stakeholder Alignment Meeting | Team Lead | May 17, 2024 | Pending | Schedule confirmed for Zoom.
4 | Tool & Automation Setup | IT Specialist | May 24, 2024 | Not Started | Configuring workflow software.
5 | Pilot Run & Feedback Collection | Operations Team | June 7, 2024 | Planned | Will run with QA team.
6 | Full Rollout & Training | HR & Onboarding Lead | June 25, 2024 | Not Started | Training materials in development.
7 | Performance Review & Optimization | Project Manager | July 5, 2024 | Not Started | Metrics to be defined post-pilot.