## Worksheet
Workflow Step | Responsible Party | Due Date | Approval Required? | Status | Notes
Initiation | Project Manager | 01/05/2024 | No | Completed | Process approved by executive team.
Requirement Gathering | Business Analysts | 01/15/2024 | Yes | In Progress | Meeting scheduled with stakeholders on Jan 14.
Design Phase | UX & Product Design Team | 02/01/2024 | Yes | Pending Approval | Final design to be reviewed by leadership.
Development | Engineering Team | 03/01/2024 | No | Not Started | Development environment ready for access.
Testing & QA | QA Team | 03/15/2024 | Yes | Not Started | Test cases to be finalized by Feb 28.
Deployment | IT Operations | 04/05/2024 | Yes | Planned | Rollout to production with rollback plan.
Post-Implementation Review | Project Manager & Stakeholders | 04/30/2024 | Yes | Not Started | Feedback collection to be completed by April 25.