## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Notes
Requirement Gathering | Project Manager | 2024-03-15 | Completed | Stakeholder interviews conducted.
Process Mapping | Operations Lead | 2024-03-20 | In Progress | Draft maps reviewed by team.
Gap Analysis | Business Analyst | 2024-03-25 | Not Started | Awaiting process mapping final version.
Optimization Plan Development | Strategy Team | 2024-04-05 | Planned | Initial proposals in draft phase.
Pilot Implementation | Operations Team | 2024-04-15 | Pending Approval | Needs executive sign-off.