## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Completion Time (Hours) | Notes / Remarks
Workflow Initiation | Project Manager | 01/05/2024 | Completed | 1.5 | Process approved and documentation finalized.
Requirement Gathering | Business Analyst | 01/12/2024 | In Progress | 3 | Stakeholder interviews scheduled for next week.
Process Design & Mapping | Process Designer | 02/01/2024 | Pending | 5 | Design draft submitted for review.
System Integration Planning | IT Lead | 02/15/2024 | Not Started | - | Needs alignment with development team.
Stakeholder Review & Feedback | Project Manager | 03/01/2024 | Delayed | - | Feedback session postponed due to scheduling conflict.
Workflow Testing & Validation | QA Team | 03/15/2024 | Not Started | - | Test environment ready upon approval.