## Worksheet
Page | Section | Workflow Step | Responsible Party | Timeline (Days) | Status | Notes
1 | Initiation | Define Objectives | Project Manager | 3 | Completed
1 | Initiation | Stakeholder Alignment | Business Lead | 5 | In Progress
2 | Design | Process Mapping | Process Analyst | 7 | Pending
2 | Design | RACI Matrix Development | Operations Manager | 5 | Not Started
3 | Implementation | Tool Selection & Setup | IT Director | 10 | Planned
3 | Implementation | Pilot Run Execution | Team Lead | 14 | Not Started
4 | Review & Optimization | Performance Metrics Setup | Data Analyst | 6 | Pending
4 | Review & Optimization | Feedback Loop Integration | Customer Experience Team | 8 | Not Started