## Worksheet
Workflow Step | Responsible Party | Deadline | Documentation Required | Status | Action Notes
Initiation & Requirement Gathering | Project Manager | Week 1, Day 5 | Stakeholder Input Form, Business Need Summary | Completed | All stakeholders provided feedback via email.
Process Mapping & Analysis | Process Analyst | Week 2, Day 3 | Process Flow Diagram, Key Pain Points Report | In Progress | Finalizing current workflow with input from operations team.
Solution Design & Proposal | Lead Designer & PM | Week 3, Day 7 | Design Mockup, Cost-Benefit Analysis | Pending Review | Awaiting sign-off from Finance and Operations.
Pilot Implementation | IT Team & Operations Lead | Week 4, Day 5 | Pilot Logs, User Feedback Summary | Not Started | Scheduled to begin after final design approval.
Full-Scale Rollout | Executive Sponsor & PMO | Week 6, Day 1 | Rollout Plan, Training Schedule | Planned | Training materials to be finalized by Week 5.
Post-Implementation Review | Project Manager & Quality Analyst | Week 8, Day 3 | KPI Report, Lessons Learned Summary | Not Started | Will evaluate efficiency gains and user adoption.