## Worksheet
Workflow Stage | Responsible Party | Timeline (Days) | Key Deliverables | Dependencies | Risks & Mitigation
Initiation | Project Sponsor | 5 | Stakeholder Alignment Document, Project Charter | None | Lack of buy-in – Mitigation via early engagement workshops
Requirements Gathering | Business Analysts | 10 | Detailed Requirements Specification, User Stories | Initiation completion | Incomplete inputs – Mitigation via iterative validation sessions
Process Design | Process Engineers | 12 | Flowcharts, Process Maps, RACI Matrix | Requirements finalization | Scope creep – Mitigation via change control board review
Implementation Planning | Project Manager | 7 | Resource Allocation Plan, Risk Register, Gantt Chart | Process Design completion | Resource unavailability – Mitigation via cross-training and backup planning
Execution & Monitoring | Cross-functional Team | 30 | Progress Reports, KPIs, Change Logs | Implementation planning approved | Delays – Mitigation via weekly review meetings and reallocation
Review & Optimization | Project Steering Committee | 5 | Post-implementation Review, Process Improvement Plan | Execution & Monitoring completed | Poor adoption – Mitigation via feedback collection and training sessions