## Worksheet
Workflow Step | Responsible Team | Target Completion Date | Current Status | Progress (%) | Notes & Actions
Requirement Gathering | Product & Business Analysis | 2024-03-15 | Completed | 100% | Final requirements approved by stakeholders.
Process Mapping & Flow Design | Operations & Process Engineering | 2024-04-10 | In Progress | 75% | Final workflow diagram scheduled for review on 2024-04-05.
Automation Pilot Implementation | IT & Technology Team | 2024-05-15 | Pending Approval | 20% | Waiting on budget sign-off from Finance.
Stakeholder Training & Onboarding | HR & Change Management | 2024-06-01 | Not Started | 0% | Schedule to be finalized post-automation launch.
Performance Review & Optimization | Analytics & Operations | 2024-07-30 | Not Started | 0% | Data collection phase to begin in Q3.